## UI tracker
YOURMAHABALESHWAR — Mobile UI tracker
Restyle code/mobile to match the website look. Keep the booking, payment, and vendor behavior already built. Do not WebView the website. Admin stays on the website.
Section | Sub-Section | Item / Task | Website screen | Mobile file today | Status | Priority | Phase | Expected result | Notes
Shared | Theme | Shared colors, type, buttons, and cards | Website green, cards, and buttons | constants/theme.js, components/ui.jsx | Done | High | 1 - Foundation | The phone kit uses website navy #003580, action blue #0071C2, gold #FFB700, page background #F0F4F8, white cards, Inter, and the website button and input styles. Later screens reuse this kit. | Shared kit only. Home layout is row 6. Pending status text uses warning #B45309 so it stays readable on white.
Customer | Home | Home screen | pages/public/HomePage.jsx | screens/customer/HomeScreen.jsx | Done | High | 2 - Customer | Photo hero with badges, headline, stats (450+ / 12k+ / 4.8), search, quick links, sponsored ads, then category strip, deals, property tabs, promo, destinations, services, and why book. | Category taps still open the same catalogs, including strawberries, Mapro, and combos. Search still opens Search. Sponsored cards use the homepage ads API.
Customer | Browse | Category list and listing cards | components/property/PropertyCard.jsx | screens/customer/CatalogScreen.jsx | Done | High | 2 - Customer | Each listing is a photo card with name, place, price, and a tap that opens the detail screen. | Photo cards show name, place, and price and open the listing. Taxi, driver, and horse rate charts stay above the cards.
Customer | Detail | Listing detail | Public detail pages | screens/customer/ListingDetailScreen.jsx | Done | High | 2 - Customer | Cover photo, title, place, price, and the booking block read as one listing page. | Cover, title, place, and price sit in one listing card. Booking fields, chart prices, and validation are unchanged.
Customer | Book | Booking and order forms | Website booking forms | screens/customer/ListingDetailScreen.jsx | Done | High | 2 - Customer | The book, order, and combo sections follow the website field order and show the same total. | Stay, trip, shop, and combo forms use the website section order. Subtotal and total are the same amount. Booking fields, chart prices, and checks are unchanged.
Customer | Search | Search | pages/public/SearchPage.jsx | screens/customer/SearchScreen.jsx | Done | Medium | 2 - Customer | A search field and result cards, with a clear empty state. | Navy search bar and listing cards. An empty search shows a clear message. Each result still opens the same listing.
Customer | Bookings | My bookings | components/booking/BookingsList.jsx | screens/customer/BookingsScreen.jsx | Done | High | 2 - Customer | Each booking shows title, status, dates, and total, with the same pay, invoice, refund, arrival, and end actions. | Each booking card shows the title, status badge, date, and total. Pay, invoice, refund, arrival, and end actions are unchanged, including vendor overtime.
Customer | Account | Account, profile, and saved listings | CustomerProfile.jsx, CustomerFavorites.jsx | AccountScreen.jsx, FavoritesScreen.jsx | Done | Medium | 2 - Customer | Profile edits name, email, and phone. Saved listings reopen the listing. | Profile still edits name, email, and phone. Saved rows still open the listing. Language and sign-out stay.
Customer | Auth | Sign in and register | Login, register, vendor register, forgot password pages | LoginScreen.jsx, RegisterScreen.jsx, VendorRegisterScreen.jsx, ForgotPasswordScreen.jsx | Done | Medium | 2 - Customer | Sign in, customer register, vendor register, and forgot password use the same fields and steps in the website layout. | Sign in, register, vendor register, and forgot password share the website card. Fields and the OTP step are unchanged.
Customer | Content | About, contact, FAQ, and policies | Public content pages | screens/customer/ContentScreen.jsx | Done | Low | 2 - Customer | About, contact, FAQ, blogs, and policies use the website headings and readable sections. | About, contact, FAQ, blogs, and policies use the website navy heading and section cards. FAQ and blogs still come from the same API.
Vendor | Hub | Vendor hub, wallet, and subscription | VendorOverview.jsx, VendorWallet.jsx, subscription pages | VendorHubScreen.jsx, VendorSubscriptionScreen.jsx | Done | Medium | 3 - Vendor | The hub shows balance, points, plan, transactions, and the same menu. Subscription pay stays on its screen. | Hub shows balance, points, plan, transactions, and the same menu. Subscription pay and Razorpay renewal stay on the subscription screen.
Vendor | Listings | Vendor listings, prices, and dates | VendorListings, VendorListingForm, VendorPricing, VendorAvailability | VendorListingsScreen.jsx, VendorListingFormScreen.jsx, VendorPricingScreen.jsx, VendorAvailabilityScreen.jsx | Done | Medium | 3 - Vendor | The list, create and edit form, price editor, and date calendar use the shared cards. | Listings, the create and edit form, prices, and the date calendar use the shared cards. Create, edit, price save, and blocked dates are unchanged.
Vendor | Tools | KYC, reviews, and homepage ads | VendorKYC.jsx, VendorReviews.jsx, VendorAdvertisements.jsx | VendorKycScreen.jsx, VendorReviewsScreen.jsx, VendorAdsScreen.jsx | Done | Low | 3 - Vendor | KYC, reviews, and homepage ads use the shared form and list layout. | KYC, reviews, and homepage ads use the shared form and list cards. Submit, the review list, and ad payment are unchanged. Document photos stay on the website.

## How to use
How to use this tracker
Continue in code/mobile. This pass changes look only.
Work in sheet order. The first task is row 5, then row 6, then the rest.
A row is Done only when that phone screen matches the website screen named in the row.
Partial means the screen is closer but a listed section is still missing.
Do not change booking payloads, prices, payments, or vendor rules while restyling.
Do not load the website inside a WebView.
Admin stays on the website.
Change Status on the UI tracker sheet. The dropdown is Done, Partial, Not started, Out of scope.