## 00 Overview
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
SM Enterprises / yourmahabaleshwar.com — Remaining Work Implementation Tracker
Source: SRS v1.0 (06 Aug 2026) + codebase review 17 Aug 2026 + tech-lead notes (Resort/Taxi merge, campaigns, refunds, reports). Website first, then Android. Only remaining / partial work is listed — completed marketplace features are out of scope here.
Sheet | Scope | Item Count | Phase | Why it is here
01 Vendor-Self-Service | Website P0: vendor listings, pricing, calendar, reviews | 12 | Website P0 | Vendor cannot self-manage listings/prices/calendar (SRS 4.3).
02 Auth-i18n | Password reset, session hardening, Marathi | 9 | Website P0–P1 | Reset page missing; Marathi incomplete; register role hole.
03 Checkout-Payments | Coupons, unified pay, live Razorpay/SMS/email/WhatsApp | 8 | Website P0 | Coupons unused at checkout; live keys; payment path inconsistent.
04 Entity-Splits | Tech lead: Resort vs Hotel, Taxi vs Driver | 9 | Website P1 | Tech lead: Resort is Hotel flag; Taxi folded into Driver.
05 Campaigns | Tech lead: real campaign module + scheduler | 5 | Website P1 | Tech lead: Campaign model, generic controller, no scheduled send job.
06 Refunds-Cancellation | Tech lead: refundService + admin process | 5 | Website P0–P1 | Tech lead: refund fields exist; logic inline; admin approve incomplete.
07 Reports | Tech lead: 10 distinct SRS report types | 5 | Website P1 | Tech lead: 10 SRS reports; generic export; no commission type.
08 CMS-Ads-Production | Search ads, blogs, legal, KYC, hardening | 13 | Website P1 / Later | Sponsored search, blogs, legal, product KYC, ops hardening.
09 Android-Customer | Play Store customer app remaining work | 8 | Android | Expo app started; Play Store + native Razorpay remaining.
10 Android-Vendor | Vendor app remaining work | 6 | Android | Vendor mobile: KYC photos, listings, vendor-safe wallet APIs.
11 Phases-Acceptance | UAT and go-live gates | 8 | Website + Android | UAT and production go-live gates.
TOTAL TASKS |  | 88
HOW TO USE
1. Do Website P0 sheets (01–03, plus refunds approve in 06) before Android.
2. Status dropdown: Not Started ¦ In Progress ¦ Blocked ¦ Partial ¦ Done. Assigned Dev is TBD until named.
3. Tech-lead items are sheets 04–07 — confirm Resort/Taxi split decision before building sheet 04 split tasks.
4. One task at a time: DB/API first, then Frontend/Android. Detail column is the acceptance check.
5. Do not reopen completed marketplace (browse/book/invoice/admin CMS) unless a remaining task depends on it.
6. After a task is Done, note PR / date in Notes.

## 01 Vendor-Self-Service
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
VENDOR DASHBOARD — LISTING SELF-MANAGEMENT
Vendor listings | API | GET /api/{vertical}/mine returns vendor-owned listings for all 8 types | Backend | Hotel, resort, homestay, tent, guide, taxi/driver, horse, product. One consistent shape (id, name, slug, prices, isActive). | Not Started | TBD | Critical | Website P0 | Some /mine routes exist (tents/guides). Hotels/resorts/homestays/horses/products need the same pattern.
Vendor listings | API | POST/PUT/DELETE vendor listing CRUD scoped to logged-in vendor | Backend | Vendor can only mutate own listings. SUPER_ADMIN still has full access. Reject cross-vendor edits with 403. | Not Started | TBD | Critical | Website P0 | CRUD exists on admin/public vendor roles but vendor dashboard does not use it.
Vendor listings | Frontend | Vendor Listings page — list my properties/services | Frontend | /dashboard/vendor/listings shows cards/table for the vendor's vertical. Empty state + Create button. | Not Started | TBD | Critical | Website P0 | Currently no listing UI on /dashboard/vendor.
Vendor listings | Frontend | Vendor Listing create/edit form (hotel/resort rooms, tent, etc.) | Frontend | Form matches vertical: hotel/resort rooms+amenities, tent capacity, guide 6hr/12hr, driver vehicle+fares, horse routes, product stock/price. | Not Started | TBD | Critical | Website P0 | Admin PropertyFormPage can be reused/adapted; do not require listing ID paste.
Vendor listings | Frontend | Role-specific vendor nav (hotel vs tent vs guide vs driver vs horse vs product) | Frontend | Sidebar only shows modules for that role. Optional: keep one layout, different menu items — not 8 separate apps. | Not Started | TBD | High | Website P0 | SRS asked for separate dashboards; shared shell + role nav is acceptable if each vertical can self-manage.
VENDOR DASHBOARD — PRICING
Pricing | API | PATCH listing prices (base, seasonal, packages, add-ons) by vendor | Backend | Hotel room price, tent/night, guide packages, taxi trip/hourly, horse route price, product price/stock. Validate numbers > 0. | Not Started | TBD | High | Website P0 | Fields already on models; need vendor-safe endpoint + UI.
Pricing | Frontend | Vendor Pricing page — edit rates without opening admin | Frontend | /dashboard/vendor/pricing loads own listings and inline-edits prices. Save toasts + validation errors. | Not Started | TBD | High | Website P0
VENDOR DASHBOARD — AVAILABILITY CALENDAR
Availability | API | GET availability for vendor-owned listings (no client-supplied listing ID required) | Backend | Resolve listings from req.user. Return blockedDates + booked dates for next 90 days per listing. | Not Started | TBD | Critical | Website P0 | GET /availability/:type/:id exists; vendor UI currently asks for listing ID.
Availability | API | PATCH block/unblock dates for vendor-owned listing only | Backend | action add/remove; 403 if listing not owned. Support hotel rooms, tents, homestays, horses, guides, drivers. | Not Started | TBD | Critical | Website P0 | Current UI only covers tent/homestay/horse/room.
Availability | Frontend | Month calendar UI — select listing from dropdown, click dates to block | Frontend | No manual listing ID. Month grid, blocked vs booked vs free. Works on mobile web. | Not Started | TBD | Critical | Website P0 | Replace VendorAvailability.jsx listing-ID form.
VENDOR DASHBOARD — REVIEWS
Reviews | API | GET /api/reviews/vendor — reviews on my listings | Backend | Paginated; include listing name, rating, comment, booking ref, isApproved. | Not Started | TBD | High | Website P1 | Reviews exist; moderation is admin-only.
Reviews | Frontend | Vendor Reviews inbox | Frontend | /dashboard/vendor/reviews list. Read-only (reply optional later). Link to listing. | Not Started | TBD | High | Website P1

## 02 Auth-i18n
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
PASSWORD RESET
Auth | Backend | Forgot-password email contains clickable frontend reset URL | Backend | Token in link: {CLIENT_URL}/reset-password?token=... Do not put raw token as the only email body. | Not Started | TBD | Critical | Website P0 | POST /auth/forgot-password exists; email currently dumps raw token.
Auth | Frontend | Reset password page /reset-password | Frontend | Read token from query; new password + confirm; POST /auth/reset-password; success → login. | Not Started | TBD | Critical | Website P0 | ForgotPasswordPage exists; no ResetPassword page in App.jsx.
OTP / SESSION
Auth | Backend | Refresh token must match stored user.refreshToken | Backend | POST /api/auth/refresh rejects reused/stolen refresh tokens. Logout still clears stored token. | Not Started | TBD | High | Website P1 | Refresh currently verifies JWT signature only.
Auth | Backend | Block self-assign of SUPER_ADMIN / staff roles on public register | Backend | POST /auth/register only allows CUSTOMER (or omit role). Vendor register stays on /register-vendor. | Not Started | TBD | High | Website P0 | Register currently accepts role from body.
Auth | Backend | Optional: OTP on admin/staff login (SRS says every login) | Backend | If product confirms SRS literally: SUPER_ADMIN and OFFICE_STAFF also get OTP. Else document exception in Notes after tech-lead sign-off. | Not Started | TBD | Medium | Website P1 | Today admin is password-only by design.
MARATHI / i18n
i18n | Frontend | Expand mr.json for public pages (home, listings, detail, search, footer, legal) | Frontend | Toggle EN/MR actually translates listing pages, not only nav/auth. | Not Started | TBD | High | Website P1 | Locale files cover nav/auth/common only.
i18n | Frontend | Translate booking forms, checkout, customer dashboard | Frontend | HotelBookingForm, ServiceBookingForm, BookingsList, invoices labels, toasts. | Not Started | TBD | High | Website P1
i18n | Frontend | Translate vendor dashboard + KYC form | Frontend | All /dashboard/vendor strings via i18n keys. | Not Started | TBD | Medium | Website P1
i18n | Frontend | Bilingual CMS fields used on public site (banner/FAQ/blog title+body EN/MR) | Frontend | If CMS has bilingual columns, public pages render active language. If not, add titleMr/bodyMr or document English-only CMS. | Not Started | TBD | Medium | Website P1 | Banner model already has bilingual title fields — wire them.

## 03 Checkout-Payments
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
COUPONS AT CHECKOUT
Coupons | Backend | POST /api/coupons/validate {code, bookingType, subtotal} | Backend | Return discount amount. Honour PERCENT/FLAT, validity dates, applicableTypes, min order, usage limits. | Not Started | TBD | Critical | Website P0 | Coupon model + admin CRUD exist; checkout does not apply codes.
Coupons | Backend | Apply coupon on booking create and persist on Booking | Backend | Fields: couponCode, discountAmount. Recalculate GST/total after discount. Reject invalid/expired codes. | Not Started | TBD | Critical | Website P0
Coupons | Frontend | Coupon input on all booking/checkout forms | Frontend | Hotels, services, products, combos. Show discount line + new total. Error if invalid. | Not Started | TBD | Critical | Website P0
UNIFIED PAYMENT FLOW
Payments | Frontend | Same pay-now path for hotel, product, combo as for service bookings | Frontend | After create booking, call payForBooking() (Razorpay or mock) OR clearly Pay now on success screen. Sticky Reserve must not dump to dashboard. | Not Started | TBD | High | Website P0 | Hotels/products/combos currently pay later from My Bookings.
Payments | Frontend | Wire StickyReservation / Heart on hotel detail to real booking + wishlist APIs | Frontend | Reserve opens booking form or payment. Heart uses /users/wishlist like PropertyCard. | Not Started | TBD | Medium | Website P1
LIVE PROVIDERS
Integrations | Config | Production Razorpay keys + webhook secret documented and verified | Backend | create-order uses live key; webhook HMAC required; mock path disabled when NODE_ENV=production. | Not Started | TBD | Critical | Website P0 | Mock mode if keys missing — do not treat as live.
Integrations | Config | SMTP + Fast2SMS + WhatsApp production keys; fail visibly if send fails in prod | Backend | Registration, OTP, booking confirm, cancel, refund, vendor approval, payment success hit real channels when keys set. | Not Started | TBD | High | Website P0 | MSG91 is still a stub — pick Fast2SMS or implement MSG91.
Integrations | Backend | Notification events matrix — one function per SRS event | Backend | Registration, OTP, booking confirm, cancel, refund status, payment success, vendor approval, subscription expiry, promo. Log SMSLog + in-app Notification. | Not Started | TBD | High | Website P1 | Not every SRS event is guaranteed today.

## 04 Entity-Splits
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
RESORT vs HOTEL (tech lead)
Resort | DB | Type-level commission default for RESORT separate from HOTEL | DB | PlatformSettings or commission matrix: hotel % vs resort %. Listing.commissionRate still overrides. | Not Started | TBD | High | Website P1 | Hotel.type HOTEL¦RESORT; both use same commissionRate default 10. RESORT maps to HOTEL_VENDOR.
Resort | Backend | GET/PUT /api/admin/commission-rates supports HOTEL and RESORT as distinct keys | Backend | Admin can set 10% hotel / 12% resort without touching each listing. | Not Started | TBD | High | Website P1 | domainController commission uses listingType HOTEL covering both.
Resort | Backend | Vendor register + KYC uses DocumentRequirement RESORT when vendorType=RESORT | Backend | Do not silently fall back to HOTEL docs if RESORT checklist exists (GST, PAN, Aadhaar, bank, business cert — no hotel license if SRS differs). | Not Started | TBD | High | Website P1 | DocumentRequirement enum includes RESORT; registerVendor maps RESORT → HOTEL_VENDOR.
Resort | Frontend | Vendor register shows Resort as own type; admin property form keeps type flag visible | Frontend | Public /resorts listing already filters type=RESORT. Fix ResortsPage links to /resorts/:slug not /hotels/:slug. | Not Started | TBD | Medium | Website P1 | ResortsPage currently uses linkPrefix=/hotels.
Resort | DB | Optional: resort packages + activities collection (only if business still wants SRS 5.3 literally) | DB | If skipped, document that packages/activities stay on Hotel description/amenities. Get sign-off. | Not Started | TBD | Low | Later | No separate package/activity entity today.
TAXI vs DRIVER (tech lead)
Taxi/Driver | Decision | Written decision: keep merged Driver model OR split Taxi + Driver | All | If keep merged: document in SRS tracker as accepted deviation. If split: following tasks apply. | Not Started | TBD | High | Website P1 | TAXI maps to DRIVER role. One Driver model. Public taxi pages + /driver-enquiry + /hourly-enquiry.
Taxi/Driver | DB | If split: Taxi listing model (vehicle, RC, fare) separate from Driver-only (experience, languages, no vehicle) | DB | Separate commission defaults (SRS taxi vs driver). Separate KYC: taxi needs RC/insurance/permit; driver needs DL only. | Not Started | TBD | High | Website P1 | DocumentRequirement already has TAXI and DRIVER enums.
Taxi/Driver | Backend | If split: roles DRIVER vs TAXI_VENDOR (or keep DRIVER + listing type) | Backend | registerVendor TAXI ≠ DRIVER. Bookings type TAXI vs DRIVER. Enquiry still public. | Not Started | TBD | High | Website P1
Taxi/Driver | Frontend | If split: /taxi vs /drivers public catalogs and vendor dashboards | Frontend | Two listing grids. Taxi booking uses vehicle; driver booking uses person+languages. | Not Started | TBD | High | Website P1 | Skip this row if decision is keep merged.

## 05 Campaigns
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
MARKETING CAMPAIGNS (tech lead)
Campaigns | Backend | Extract services/campaignService.js from phase1bController | Backend | create, update, resolveAudience, send, stats. Controller only HTTP. No send logic left in generic controller. | Not Started | TBD | High | Website P1 | Campaign model exists; sendCampaign is a loop in phase1bController.
Campaigns | Backend | Scheduler job: send campaigns where status=SCHEDULED and scheduledAt <= now | Backend | Add to src/jobs/scheduler.js. Idempotent. Skip SENT/SENDING. Set FAILED on throw. | Not Started | TBD | High | Website P1 | scheduledAt field exists; scheduler never sends campaigns.
Campaigns | Backend | Per-channel send with retries + Campaign recipient log | Backend | Store per-user sent/fail. Email/SMS/WhatsApp use real services. In-app Notification still created. | Not Started | TBD | High | Website P1 | Stats targeted/sent/failed exist; no per-recipient log.
Campaigns | Backend | Audience segmentation: customers, vendors, role segment, last-booking filter (optional) | Backend | SEGMENT + segmentRoles already; add documented filters if marketing needs them. | Not Started | TBD | Medium | Website P1
Campaigns | Frontend | Admin campaign UI: schedule datetime, channel, audience, preview count, send/schedule, stats | Frontend | Cannot send twice. Show targeted/sent/failed. Campaign reports link. | Not Started | TBD | High | Website P1 | CampaignsPage exists — wire schedule + live stats.

## 06 Refunds-Cancellation
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
REFUND & CANCELLATION (tech lead)
Refunds | Backend | Create services/refundService.js | Backend | Move computeRefundAmount, policy lookup, Razorpay refund, booking+payment status updates out of paymentController. | Not Started | TBD | High | Website P1 | Logic is inline in paymentController.js. No refundService.
Refunds | Backend | Admin approve refund actually processes payment (or queues job) | Backend | PATCH /admin/refunds/:id approve should call refundService, not only set REQUESTED and tell client to POST /payments/refund. | Not Started | TBD | Critical | Website P0 | domain.moderateRefund currently says use POST /payments/refund.
Refunds | Backend | Customer cancel → policy preview → confirm → status + refund + notifications | Backend | Full / partial / none from listing or PlatformSettings (48h/24h/50% defaults). refundStatus REQUESTED¦PROCESSING¦COMPLETED¦REJECTED. | Not Started | TBD | High | Website P0 | Preview+request exist; notifications not guaranteed on all channels.
Refunds | Frontend | Customer cancel/refund UI shows policy amount before confirm | Frontend | BookingsList refund preview already — show full/partial/none copy. After submit, show refundStatus. | Not Started | TBD | High | Website P0
Refunds | Frontend | Admin refunds queue: filter status, approve (processes), reject with reason | Frontend | Must not require a second hidden API call. Audit log the action. | Not Started | TBD | High | Website P0

## 07 Reports
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
REPORTS — 10 SRS TYPES (tech lead)
Reports | Backend | Dedicated commission report (not a column on bookings dump) | Backend | GET /admin/reports/hub/export?type=commission — vendor, bookingNumber, subtotal, commission %, commission amount, payout status, date range. | Not Started | TBD | High | Website P1 | SRS lists Commission Reports. Export types today: bookings, revenue, gst, refunds, payments, subscriptions, ads, vendors, customers. No commission type.
Reports | Backend | Distinct queries for Booking / Revenue / GST / Refund reports | Backend | Do not reuse one Booking.find map for all four. Revenue = paid totals; GST = gst breakdown; Refunds = refunded rows with gateway ids; Bookings = operational status. | Not Started | TBD | High | Website P1 | exportController uses the same booking dump for bookings/revenue/gst/refunds.
Reports | Backend | Payment report includes method, Razorpay ids, refundedAmount, bookingNumber | Backend | Join Payment→Booking. Date filter. Limit documented. | Not Started | TBD | Medium | Website P1 | Payments export exists; no bookingNumber join.
Reports | Backend | Vendor report includes KYC status, listing counts, wallet, points, commission owed | Backend | More than User.find vendors. Needed for settlements. | Not Started | TBD | Medium | Website P1 | Current vendor export is a thin user list.
Reports | Frontend | Reports Hub: 10 export buttons matching SRS names | Frontend | Booking, Vendor, Customer, Revenue, Commission, GST, Refund, Subscription, Advertisement, Payment. Date range applies to all. | Not Started | TBD | High | Website P1 | EXPORT_TYPES has 9 labels; missing Commission.

## 08 CMS-Ads-Production
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
ADS / SEARCH PRIORITY
Ads | Backend | Search and listing APIs boost sponsored/featured listings | Backend | Active Advertisement or isFeatured sorts first (then rating/date). Do not bury paid listings. | Not Started | TBD | High | Website P1 | featured=true filter exists; search does not auto-rank sponsored.
Ads | Frontend | Sponsored badge on listing cards + homepage banners from CMS | Frontend | Public cards show Sponsored when ad/featured. HomePromoBanner uses /admin/public/banners. | Not Started | TBD | Medium | Website P1
CMS / PUBLIC PAGES
CMS | Frontend | Public blog detail route /blogs/:slug | Frontend | Fetch blog by slug; SEO title; related posts optional. | Not Started | TBD | Medium | Website P1 | Blogs list has no detail page.
CMS | Frontend | Replace placeholder Privacy / Terms / Cancellation copy from CMS or static real text | Frontend | Legal pages must not be one-paragraph stubs before go-live. | Not Started | TBD | Medium | Website P1
CMS | Frontend | Search page renders guides, drivers, products, combos (not only stays) | Frontend | globalSearch already fetches them — show result groups. | Not Started | TBD | Medium | Website P1
CMS | Frontend | Map placeholder: hide or integrate maps; do not ship 'integrate Google Maps' stub | Frontend | Either Google/Mapbox key or remove map tab. | Not Started | TBD | Low | Later
KYC / ROLES
KYC | Backend | PRODUCT_VENDOR document checklist (not hotel fallback) | Backend | DocumentRequirement PRODUCT or STRAWBERRY/MAPRO docs. VendorKYC uses it. | Not Started | TBD | Medium | Website P1 | Product vendor KYC falls back to HOTEL docs.
KYC | Frontend | Login redirect PRODUCT_VENDOR → /dashboard/vendor (not /) | Frontend | LoginPage roleRedirect include PRODUCT_VENDOR. | Not Started | TBD | High | Website P0 | Falls through to home today.
PRODUCTION HARDENING
Ops | Backend | Await connectDB before app.listen; fail fast on Mongo error | Backend | No request hits API until mongoose connected. | Not Started | TBD | Medium | Website P1 | connectDB() is fire-and-forget in server.js.
Ops | Backend | Add firebase-admin to package.json OR remove FCM dynamic import | Backend | Push must not crash if package missing. Document Expo-only vs FCM. | Not Started | TBD | Medium | Website P1 | pushService dynamically imports firebase-admin; not in package.json.
Ops | DevOps | CI/CD pipeline (lint + test smoke + docker build) | All | GitHub Actions or agreed CI. Block merge on lint. | Not Started | TBD | Medium | Later | No .github workflows today.
Ops | DevOps | Error monitoring (Sentry or equivalent) on API + web | All | Capture 5xx and frontend crashes in production. | Not Started | TBD | Medium | Later
Ops | Backend | Encrypt or hash sensitive KYC numbers at rest (Aadhaar/PAN) if required | Backend | Confirm with tech lead. If yes: encrypt fields, decrypt only for admin KYC view. | Not Started | TBD | Medium | Later | No field-level encryption today.

## 09 Android-Customer
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
ANDROID CUSTOMER APP
Android | Mobile | EAS project + eas.json production profile | Android | eas build --platform android --profile production. Bundle ID com.smenterprises.yourmahabaleshwar. | Not Started | TBD | Critical | Android | No eas.json today.
Android | Mobile | google-services.json + notification credentials for Play build | Android | FCM/Expo push works on real devices. | Not Started | TBD | High | Android
Android | Mobile | Native Razorpay checkout (react-native-razorpay) on custom dev/prod client | Android | Stop mock-verify when keyId is live. Success → POST /payments/verify with real signatures. | Not Started | TBD | Critical | Android | BookingsScreen always mock-verifies today.
Android | Mobile | Hotel room picker (do not auto-pick rooms[0]) | Android | ListingDetailScreen shows rooms and prices; booking body includes selected room. | Not Started | TBD | High | Android
Android | Mobile | Catalog search + filters | Android | Query, dates, price, vertical chips. Uses existing listing query params. | Not Started | TBD | High | Android | Catalog is a flat list.
Android | Mobile | In-app notification inbox (GET /users/notifications) | Android | List + mark read. Push tap opens booking or listing. | Not Started | TBD | High | Android | getNotifications exists in endpoints.js but unused.
Android | Mobile | Password reset + coupon + wishlist if web has them | Android | Parity with website P0 checkout/auth once those APIs exist. | Not Started | TBD | Medium | Android
Android | Mobile | Play Store listing, screenshots, privacy policy URL, production API URL | Android | EXPO_PUBLIC_API_URL=https://www.yourmahabaleshwar.com/api | Not Started | TBD | High | Android

## 10 Android-Vendor
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
ANDROID VENDOR APP
Android vendor | Mobile | KYC document capture (camera/gallery) multipart upload | Android | Use expo-image-picker; POST /users/kyc FormData matching web fields. | Not Started | TBD | Critical | Android | VendorKycScreen is text-only.
Android vendor | Mobile | Vendor listing list + create/edit (reuse website APIs) | Android | Depends on Website P0 listing APIs. Minimum: view + toggle isActive + edit price. | Not Started | TBD | Critical | Android | No listing CRUD on mobile.
Android vendor | Mobile | Vendor availability calendar | Android | Same APIs as website calendar. Block/unblock dates. | Not Started | TBD | High | Android
Android vendor | Mobile | Wallet, points purchase, subscription status using vendor-safe APIs (not admin-only) | Android | If /admin/wallet is admin-gated, add /api/vendor/wallet. Mobile must not 403 for vendors. | Not Started | TBD | High | Android | VendorHub uses /admin/wallet and /admin/subscriptions/me.
Android vendor | Mobile | PRODUCT_VENDOR (and all 8 types) can register and see vendor tab | Android | VendorRegisterScreen types include PRODUCT. VENDOR_ROLES includes PRODUCT_VENDOR. | Not Started | TBD | Medium | Android | Mobile vendor types omit PRODUCT today.
Android vendor | Mobile | Accept/reject bookings remains working after API changes | Android | Regression: vendor BookingsScreen status patch + points/subscription errors shown. | Not Started | TBD | High | Android | Already works in dev against current API.

## 11 Phases-Acceptance
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
WEBSITE UAT
UAT | QA | Seed demo accounts still work after remaining features | All | Admin, customer, each vendor type. OTP in non-prod. Document credentials. | Not Started | TBD | High | Website P0 | npm run seed in backend.
UAT | QA | E2E: search → book → pay (test Razorpay) → invoice → vendor accept → complete | All | Run for hotel, resort, homestay, tent, guide, taxi, horse, product, combo. | Not Started | TBD | Critical | Website P0
UAT | QA | E2E: coupon apply, cancel/refund full+partial+none, KYC approve, campaign send | All | Record screenshots for tech lead. | Not Started | TBD | Critical | Website P1
UAT | QA | Marathi toggle smoke on home + one booking form + vendor KYC | Frontend | No missing-key dumps like 'nav.stays'. | Not Started | TBD | Medium | Website P1
ANDROID UAT
UAT | QA | Device UAT: OTP, browse 10 verticals, book, live pay, invoice, push | Android | Physical Android device, production or staging API. | Not Started | TBD | Critical | Android
UAT | QA | Vendor device UAT: KYC upload, accept booking, wallet visible | Android |  | Not Started | TBD | Critical | Android
GO-LIVE
Go-live | DevOps | Production docker-compose + nginx TLS smoke (www + /api/health + /healthz) | All | Follow docs/PRODUCTION.md. Apex → www 301. | Not Started | TBD | Critical | Later
Go-live | All | Tech-lead sign-off on merged Resort/Taxi decision + remaining tracker 100% Done or accepted Partial | All | Update this workbook Status column. Attach SRS HTML report. | Not Started | TBD | High | Later