## Mobile tracker
YOURMAHABALESHWAR — Mobile app implementation tracker
Customer and vendor only. Continue in code/mobile. Match each row to the website screen. Admin stays on the website.
Section | Sub-Section | Item / Task | Website screen | Mobile file today | Status | Priority | Phase | Expected result | Notes
Foundation | App shell | Keep Expo app in code/mobile | — | code/mobile | Done | High | 0 - Foundation | Same Android package and iOS bundle ID. Do not start a new app folder. | Admin is out of scope.
Foundation | API | API client pointed at the backend | frontend/src/services/api.js | mobile/src/api/client.js | Done | High | 0 - Foundation | Customer and vendor calls use the same API as the website.
Foundation | Navigation | Customer tabs and vendor tab only | frontend/src/App.jsx | mobile/src/navigation/RootNavigator.jsx | Done | High | 0 - Foundation | Home, bookings, account, and a vendor tab for vendor roles. No admin routes.
Foundation | Language | English and Marathi | frontend i18n | mobile/src/i18n | Done | Medium | 0 - Foundation | User can switch language from Account.
Foundation | Push | Register device for push | — | mobile/src/services/push.js | Done | Low | 0 - Foundation | After login or OTP, the phone token is saved on the account. Logout removes it. Firebase delivery stays for later. | Needs a real Expo project UUID in app.json extra.eas.projectId and a physical device. Placeholder ids are ignored.
Auth | Login | Email and password, then SMS OTP | pages/auth/LoginPage.jsx | screens/auth/LoginScreen.jsx | Done | High | 0 - Foundation | Customer lands on Home. Vendor lands on the vendor tab. OTP is required after the password, same as the website. | Forgot password is row 13.
Auth | Customer signup | Name, email, phone, password, then OTP | pages/auth/RegisterPage.jsx | screens/auth/RegisterScreen.jsx | Done | High | 0 - Foundation | Name, email, 10-digit phone, and password create the account. Phone OTP verifies it and opens Home. | Password must match and be at least 6 characters, same as the website.
Auth | Vendor signup | Vendor registration with role | pages/auth/VendorRegisterPage.jsx | screens/auth/VendorRegisterScreen.jsx | Done | High | 0 - Foundation | Vendor picks a business type, verifies the phone OTP, then opens the vendor tab. Shop vendors open KYC. | Creating the listing form is a later row. Driver and shop types are included.
Auth | Password | Forgot password | pages/auth/ForgotPasswordPage.jsx | screens/auth/ForgotPasswordScreen.jsx | Done | Medium | 0 - Foundation | From login, the user enters an email and the app requests a password reset, same as the website. | The email is sent only after SMTP is configured.
Customer browse | Home | Category grid matching the website | pages/public/HomePage.jsx | screens/customer/HomeScreen.jsx | Done | High | 1 - Browse | Home shows hotels, resorts, homestays, tents, guides, drivers, taxi, horses, strawberries, Mapro, and combos. | Drivers tile opens the driver catalog. The dedicated driver booking flow is a later row.
Customer browse | Hotels | Hotel list and detail | pages/public/HotelsPage.jsx, HotelDetailPage.jsx | CatalogScreen.jsx, ListingDetailScreen.jsx | Done | High | 1 - Browse | Hotel list and detail show the photo, price, location, and rooms from the same API as the website. | The full guest booking form is a later row. The chosen room is sent with the booking.
Customer browse | Resorts | Resort list and detail | pages/public/ResortsPage.jsx | CatalogScreen.jsx | Done | High | 1 - Browse | Resorts are hotels filtered by type RESORT. Detail shows photo, price, location, and rooms. | Same screens as hotels. An empty resort list says nothing is here, not an error.
Customer browse | Homestays | Homestay list and detail | pages/public/HomestaysPage.jsx, HomestayDetailPage.jsx | CatalogScreen.jsx, ListingDetailScreen.jsx | Done | High | 1 - Browse | Homestay list and detail show photo, nightly price, location, facilities, check-in times, house rules, and rooms. | Guest registration form is row 29. The selected room is sent with the booking.
Customer browse | Tents | Tent list and detail | pages/public/TentsPage.jsx, TentDetailPage.jsx | CatalogScreen.jsx, ListingDetailScreen.jsx | Done | High | 1 - Browse | Tent list and detail show photo, nightly price, location, capacity, facilities, and check-in rules. | The tent guest booking form is row 30.
Customer browse | Guides | Guide list and detail | pages/public/GuidesPage.jsx, GuideDetailPage.jsx | CatalogScreen.jsx, ListingDetailScreen.jsx | Done | High | 1 - Browse | Guide list shows the 6-hour price. Detail shows this guide packages plus the official rate chart and sightseeing points. | The full guide booking form is row 31. The selected 6hr or 12hr package and bike add-on are sent with the booking.
Customer browse | Taxi | Taxi list and detail | pages/public/TaxiPage.jsx, TaxiDetailPage.jsx | CatalogScreen.jsx, ListingDetailScreen.jsx | Done | High | 1 - Browse | Taxi list loads taxi operators and shows car types plus local and outstation routes before booking. | The full taxi guest form is row 32. The selected car, route, and per-trip or hourly fare are sent with the booking.
Customer browse | Drivers | Driver list and booking entry | pages/public/DriversPage.jsx | CatalogScreen.jsx, ListingDetailScreen.jsx | Done | High | 1 - Browse | Drivers tile opens driver partners plus the booking entry: how it works and the 4hr, 8hr, and 12hr packages. | The full driver guest form is row 33. The selected package is sent with the booking.
Customer browse | Horses | Horse list and detail | pages/public/HorsesPage.jsx, HorseDetailPage.jsx | CatalogScreen.jsx, ListingDetailScreen.jsx | Done | High | 1 - Browse | Horse list and detail show the official ride packages plus each stable routes, duration, and price. | The full horse guest form is row 34. The selected route is sent with the booking.
Customer browse | Shop | Strawberry products | pages/public/ProductsPage.jsx | CatalogScreen.jsx | Done | Medium | 1 - Browse | Strawberry products list shows the photo, short description, price, and unit from the same products API as the website. | Ordering with quantity is row 35.
Customer browse | Shop | Mapro products | pages/public/ProductsPage.jsx | CatalogScreen.jsx | Partial | Medium | 1 - Browse | Mapro products list with price and photo.
Customer browse | Shop | Combos | pages/public/CombosPage.jsx, ComboDetailPage.jsx | CatalogScreen.jsx, ListingDetailScreen.jsx | Partial | Medium | 1 - Browse | Combo contents and price match the website.
Customer browse | Search | Global search | pages/public/SearchPage.jsx | — | Not started | Medium | 1 - Browse | Search finds listings across services.
Customer browse | Content | About, contact, FAQ, blogs, policies | pages/public About, Contact, Faq, Blogs, StaticPage | — | Not started | Low | 1 - Browse | Static pages open inside the app. | Do these after booking works.
Customer booking | Stays | Hotel and resort booking | Hotel detail booking | ListingDetailScreen.jsx | Partial | High | 2 - Book and pay | Dates, guests, and room choice create the same booking as the website. | Current form always uses the first room.
Customer booking | Stays | Homestay booking | HomestayDetailPage.jsx | ListingDetailScreen.jsx | Partial | High | 2 - Book and pay | Dates and guests match the website rules.
Customer booking | Stays | Tent booking | pages/TentBookingPage.jsx | ListingDetailScreen.jsx | Partial | High | 2 - Book and pay | Tent dates and guest count match the website.
Customer booking | Services | Guide booking with packages | pages/public/GuideBookingPage.jsx | ListingDetailScreen.jsx | Not started | High | 2 - Book and pay | Package, bike add-on, and price match the website rate chart. | App currently sends a fixed 6-hour package.
Customer booking | Services | Taxi booking with routes | pages/TaxiBookingPage.jsx | ListingDetailScreen.jsx | Not started | High | 2 - Book and pay | Route, car type, and price match the website. | App currently sends a fixed TRIP type.
Customer booking | Services | Driver booking | pages/DriverBookingPage.jsx | — | Not started | High | 2 - Book and pay | Driver package and price match the website.
Customer booking | Services | Horse booking with packages | pages/HorseBookingPage.jsx | ListingDetailScreen.jsx | Not started | High | 2 - Book and pay | Package and price match the website.
Customer booking | Shop | Product order | pages/public/ProductDetailPage.jsx | ListingDetailScreen.jsx | Partial | Medium | 2 - Book and pay | Quantity and total match the website.
Customer booking | Shop | Combo booking | pages/public/ComboDetailPage.jsx | ListingDetailScreen.jsx | Partial | Medium | 2 - Book and pay | Date and price match the website.
Customer booking | Payment | Live Razorpay checkout | Website Razorpay checkout | screens/customer/BookingsScreen.jsx | Not started | High | 2 - Book and pay | Customer pays with the live Razorpay key and the booking is marked paid. | App still verifies a mock payment.
Customer booking | After book | My bookings, invoice, refund request | dashboards/customer/CustomerBookings.jsx | screens/customer/BookingsScreen.jsx | Partial | High | 2 - Book and pay | List, status, invoice, and refund request match the website.
Customer booking | Trip | Customer confirms partner arrival and end | Customer booking actions | screens/customer/BookingsScreen.jsx | Partial | High | 2 - Book and pay | Customer can confirm arrival and service end, including overtime. | Buttons exist. Recheck against the website.
Customer account | Profile | View and edit profile | dashboards/customer/CustomerProfile.jsx | screens/customer/AccountScreen.jsx | Partial | Medium | 3 - Account | Name, email, and phone can be updated. | View only today.
Customer account | Favorites | Saved listings | dashboards/customer/CustomerFavorites.jsx | — | Not started | Low | 3 - Account | Customer can save and reopen a listing.
Vendor | Home | Wallet balance, points, subscription status | dashboards/vendor/VendorOverview.jsx, VendorWallet.jsx | screens/vendor/VendorHubScreen.jsx | Partial | High | 4 - Vendor | Vendor sees balance, points, and current subscription. | No purchase or payout history.
Vendor | KYC | Submit KYC and bank details | dashboards/vendor/VendorKYC.jsx | screens/vendor/VendorKycScreen.jsx | Partial | High | 4 - Vendor | Aadhaar, PAN, and bank details submit like the website. | No document photo upload yet.
Vendor | Listings | My listings list | dashboards/vendor/VendorListings.jsx | — | Not started | High | 4 - Vendor | Vendor sees only their own listings for their role.
Vendor | Listings | Create and edit a listing | dashboards/vendor/VendorListingForm.jsx | — | Not started | High | 4 - Vendor | Create and edit match the website form for that vendor role.
Vendor | Pricing | Set prices | dashboards/vendor/VendorPricing.jsx | — | Not started | High | 4 - Vendor | Price changes save and show on the customer listing.
Vendor | Availability | Block and open dates | dashboards/vendor/VendorAvailability.jsx | — | Not started | High | 4 - Vendor | Blocked dates cannot be booked, same as the website. | Only roles that have availability on the website.
Vendor | Bookings | Vendor booking actions | dashboards/vendor/VendorBookings.jsx | screens/customer/BookingsScreen.jsx | Partial | High | 4 - Vendor | Vendor can mark arrived, propose end, and add overtime. | Shared with the customer bookings screen.
Vendor | Reviews | Listing reviews | dashboards/vendor/VendorReviews.jsx | — | Not started | Medium | 4 - Vendor | Vendor can read reviews on their listings.
Vendor | Wallet | Wallet history and buy points | dashboards/vendor/VendorWallet.jsx | screens/vendor/VendorHubScreen.jsx | Not started | Medium | 4 - Vendor | History and point purchase match the website. | Hub shows balance only.
Vendor | Subscription | Buy or renew subscription | dashboards/vendor/VendorMySubscription.jsx | screens/vendor/VendorHubScreen.jsx | Not started | Medium | 4 - Vendor | Stay and service plans can be paid the same way as the website. | Hub shows status only.
Vendor | Ads | Homepage advertisements | dashboards/vendor/VendorAdvertisements.jsx | — | Not started | Low | 4 - Vendor | Vendor can buy a homepage ad the same way as the website.
Out of scope | Admin | Admin panel | frontend admin routes | — | Out of scope | Low | — | No admin screens in the mobile app. | Use the website admin.

## How to use
How to use this tracker
Continue in code/mobile. Do not create a second app.
Build customer and vendor only. Leave admin on the website.
Work phase by phase: 0 Foundation, 1 Browse, 2 Book and pay, 3 Account, 4 Vendor.
A row is Done only when it behaves like the website screen named in that row.
Partial means a screen exists but booking rules, layout, or payment still differ from the website.
Change Status in the Mobile tracker sheet. The dropdown is Done, Partial, Not started, Out of scope.
Filter by Phase or Status to see the next task.